## Maturity plan
Loan maturity planner
Dates work back from your maturity date. The lead times are planning assumptions: replace them with your lender's estimates.
Current loan matures on | 2027-06-30
Application to closing (days) | 75
Cushion before maturity (days) | 30
Target closing date
Application date
Step | Target date | Days from today | Status
Get payoff, prepayment and extension terms from your servicer in writing
Assemble T-12, current rent roll, capex history, entity documents
Send the package to lenders; collect term sheets
Sign the application; lender orders appraisal and third-party reports
Reports back; underwriting and loan committee
Lock the rate (timing depends on the lender's process)
Close and fund
Current loan matures
apartment.loans · Janover Capital LLC · Estimates only, not a loan quote. Replace every shaded cell with your own numbers.
Formulas:
Days from today = [Target date]-TODAY()
Status = IF([Target date]<TODAY(),"Past due","")